## WPs
WP | Title | Lead
WP1 | Project Management | LPD
WP2 | Doing stuff | LLC
WP3 | Big Trials | PLC

## Tasks
WP | ID | Title | Lead | Status | Progress | Start | Due | Notes | Risks
WP1 | D1.1 | Updates to the Gannt chart | LPD | Done | 100 | 2026-01-01 | 2026-01-30
WP1 | D1.2 | Top tear teem work | LPD/LLC | Started | 40 | 2026-02-01 | 2026-03-30 |  | Logistics
WP1 | D1.3 | Ongoing Project Management meeting between partners | LLC/LPD/PLC | Ongoing | 30 | 2026-04-01 | 2026-06-30
WP2 | D2.1a | Getting on with research. Just the one partner | LLC | Done | 100 | 2026-02-01 | 2026-03-30
WP2 | D2.1b | Getting on with research. Two partners | LLC/PLC | Delayed | 15 | 2026-01-01 | 2026-04-30
WP2 | D2.1c | Getting on with research. All three partners | LLC/LPD/PLC | Cancelled | 0 | 2026-03-01 | 2026-05-30 | Ahh noo | Logistics
WP2 | D2.2a | Getting bogged down with administration | LLC | Not Started | 0 | 2026-04-01 | 2026-05-30
WP2 | D2.2b | Getting bogged down with finances | LLC | Not started | 0 | 2026-05-01 | 2026-07-30
WP2 | D2.3a | Bits of stuff that need doing Q1 | PLC | Started | 40 | 2026-06-01 | 2026-08-30
WP2 | D2.3b | Bits of stuff that need doing Q2 | PLC | delayed | 50 | 2026-08-01 | 2026-11-10
WP2 | M1 | Binging everything together in one place | LLC | Not Started | 0 | 2026-06-01 | 2026-11-30
WP3 | D3.1a | Trailing on a big site in summer | PLC | Started | 30 | 2026-06-01 | 2026-09-30 |  | Weather
WP3 | D3.1b | Trailing on a big site in winter | PLC | Not started | 0 | 2026-10-01 | 2026-12-30 |  | Weather;Logistics
WP3 | D3.2 | Working to fix big issues | PLC/LLC | Delayed | 60 | 2026-08-01 | 2026-09-30
WP3 | D3.3a | Working on what to look at | PLC/LPD | Delayed | 20 | 2026-07-01 | 2026-08-30
WP3 | D3.3b | Working on what to sample | PLC | Not started | 0 | 2026-09-01 | 2026-10-30
WP3 | M2 | Data from the big trial | PLC | Not Started | 0 | 2026-10-01 | 2026-11-30 |  | Logistics

## Dependencies
From | To
D1.1 | D1.2
D1.3 | D2.1c
D1.2 | D1.3
D2.1a | D2.1b
D2.1b | D2.1c
D2.2a | D2.2b
D2.3a | D2.3b
D3.1a | D3.1b
D3.3a | D3.3b
D3.2 | M2
D3.3b | M2
D2.3b | M1
D2.2b | M1

## Partners
Partner | NodeColour | ClusterColour | Contact | Email | Phone | Address
LPD | [6 empty] | #VALUE!
LLC
PLC
Note on B1: Avoid theam colours. Will read # colour first.
Note on C1: Avoid theam colours. Will read # colour first.

## Statuses
Status | BorderColour | Action
Ongoing
Started
Done
Delayed
Cancelled | #DC2626
Not Started
Note on B1: Avoid theam colours. Will read # colour first.

## Risks
Name | Description | Severity | Likelihood | Mitigation | New_Severity | New_Likelihood
Logistics | We can't work together | 3 | 1 | MS teams | 2 | 1
Weather | Its bad at the moment | 2 | 3 | It will be better tomorrow | 1 | 2